# DEVELOPMENT PLAN & TEST STRATEGY

## LocalCBT v1.0 | Milestone, backlog, gates, risks

Status: Draft pengembangan · Baseline: PRD.md, TECHNICAL_DESIGN.md, DATABASE_DESIGN.md, API_SPEC.yaml, USER_FLOW.md, UI_UX_DESIGN.md.

Dokumen ini adalah rencana eksekusi, bukan bukti implementasi. Semua estimasi perlu disesuaikan dengan kapasitas tim dan perangkat sekolah nyata. Tidak ada komitmen tanggal rilis sampai technical spikes selesai.

## 1. Tujuan, scope, non-goals

Target first pilot 30 peserta aktif bersamaan, beberapa guru dan minimal 2 ujian berbeda dalam satu instalasi sekolah. Klien siswa komputer/laptop/HP (browser), guru/pengawas browser, operator server Windows/macOS melalui GUI PySide6. Jaringan ujian terisolasi dari WAN. Soal hanya teks/gambar: PG, MCMA, kategori Benar/Salah; kelas, mata pelajaran, bank soal, import XLSX/DOCX, token, individual timer, pause 5 menit per incident & 10 menit kumulatif, free nav, autosave, grading, controlled results/review, export Excel, monitoring, backups.

Tidak dibangun sebelum pilot: multi-school/cloud, esai, audio/video, scanning OCR, AI generatif, kiosk mode/SEB penuh, penguncian data seluler, proctoring webcam, integrasi resmi dinas, analytics canggih dan HA server. Dokumen PRD memberi roadmap kandidat v1.5/v2.0.

## 2. Dependency graph dan urutan kerja

flowchart LR
  A[Gate 0: sekolah/rumus/infra validation] --> B[M1: repo + service + DB + CI]
  B --> C[M2: auth + roles + academic]
  C --> D[M3: question bank + import]
  D --> E[M4: exam snapshot + grading policy]
  E --> F[M5: student exam UI + attempt + autosave]
  F --> G[M6: timer + pause + recovery]
  G --> H[M7: proctor realtime + reports + publishing]
  H --> I[M8: Control Center + backups + LAN]
  I --> J[M9: security, load, recovery, pilot]

UI/UX dapat dikerjakan paralel sejak M1 dan selesai sebelum fitur terkait diimplementasikan. API spec menjadi kontrak lintas tim; setiap perubahan field publik memerlukan penyesuaian dokumentasi, client types, dan test.

## 3. Gate 0: Validasi sebelum coding besar

- DISC-01 | Pekerjaan: Survei komputer server sekolah, OS, RAM/disk, LAN, AP/router, jumlah kelas/siswa, opsi VLAN; Bukti kelulusan: Inventaris aktual tertulis, ada operator sekolah

- DISC-02 | Pekerjaan: Validasi rumus Partial Credit oleh guru (MCMA & kategori); Bukti kelulusan: 12+ contoh input/output ditandatangani guru, decimal rounding dipilih

- DISC-03 | Pekerjaan: Tetapkan server outage & delayed offline queue policy; Bukti kelulusan: Aturan fairness tertulis, termasuk kejadian global

- DISC-04 | Pekerjaan: Uji trusted HTTPS certificate Android/iOS/Windows/macOS pada LAN tertutup; Bukti kelulusan: Semua target bisa mengakses tanpa bypass peringatan sertifikat

- DISC-05 | Pekerjaan: Prototipe installer PySide6 + FastAPI service + PostgreSQL di Win/macOS; Bukti kelulusan: GUI ditutup, backend tetap hidup; reboot recovery; uninstall bersih

- DISC-06 | Pekerjaan: Kebijakan jaringan, IPv6, separate staff/SSID dan WAN block; Bukti kelulusan: Capture hasil tes dari perangkat exam VLAN; WAN deny terbukti

- DISC-07 | Pekerjaan: Backup lifecycle, retensi data & prosedur restore sekolah; Bukti kelulusan: Owner, lokasi backup kedua, strategi kunci enkripsi, periode arsip disetujui

Go/no-go Gate 0: Jika akses mobile ke HTTPS lokal gagal, DB packaging tidak feasible, atau formula nilai tidak disahkan, jangan mengklaim M9 siap rilis; revisi desain bersama stakeholder.

## 4. Milestone detail dan definisi selesai

### M1. Repository foundation & server runtime

Backlog:

- M1-01 Monorepo struktur terpisah web/API/Control Center/docs, lint/format/typecheck.

- M1-02 FastAPI app, settings, SQLAlchemy + Alembic, PostgreSQL, health endpoint internal.

- M1-03 Reverse proxy local HTTPS proof, static assets bundling, no external font/CDN.

- M1-04 Windows/macOS service spike; GUI PySide6 status dan independent service lifecycle.

- M1-05 CI unit tests, dependency lock files, secret scanning, structured request-id logging.

Done: fresh install environment development bisa menjalankan web + API + DB, migration idempotent, GUI ditutup tidak mematikan service; test keamanan dependensi baseline dijalankan.

### M2. Account, RBAC, class/subject/student

- M2-01 Users/roles/teacher/student schema, Argon2id, server session, CSRF, login-rate-limit.

- M2-02 Matrix izin object-level untuk exam/question bank/student/result, tests IDOR.

- M2-03 Class/subject/teacher relationships, import student XLSX preview+commit.

- M2-04 Staff/student auth pages, state session expired/single active session.

Done: login NIS+password, teacher/proctor can share account roles, import invalid rows tidak membuat data parsial diam-diam, role bypass test gagal mengakses objek tanpa izin.

### M3. Bank soal + editor + DOCX/XLSX importer

- M3-01 Tiga tipe soal, validator options/statements, text/image upload validated.

- M3-02 Stimulus teks/gambar & grouping, CRUD bank soal pribadi, share permissions.

- M3-03 Import template XLSX/DOCX, parse tanpa macros, preview valid/invalid, commit.

- M3-04 Student-like preview, gambar lokal dengan izin, upload size/type limits.

Done: guru membuat 3 jenis soal, key tidak bocor ke student APIs, import template dengan error baris terukur, stimulus utuh dan sharing permission valid.

### M4. Ujian, snapshot, jadwal, grading policy

- M4-01 Draft exam: kelas, start window, duration, token hash, randomization, result policy.

- M4-02 Publish validation: immutable snapshot question/options/keys + rubric version.

- M4-03 Safe shuffling preserving key/option IDs and stimulus relationships.

- M4-04 Grading PG + MCMA/category partial credit with agreed fixtures.

- M4-05 Grade receipts, numeric precision & auditable rule versions.

Done: published exam tak berubah walau sumber edit; formula kompleks lulus fixture sekolah; token tak bocor di API log; start window validated.

### M5. Student exam engine

- M5-01 Student list/valid token/start attempt atomik unique per siswa-ujian.

- M5-02 Student exam UI responsive 360px+, free nav, answered/marked/status.

- M5-03 Save answer transactional + idempotency/revision with real-time save indicator.

- M5-04 Early submit with warnings; auto-submit by server expiry, result hidden by default.

- M5-05 Student submission receipt and server-guarded review state.

Done: tidak ada lost acknowledged answer; dua submit tak menghasilkan dua results; student API tidak mengandung correct answers/hidden results.

### M6. Individual timer, automatic pause & recovery

- M6-01 Server-authoritative individual duration; UTC time; display status.

- M6-02 Heartbeat server + disconnect incident; 300 detik per incident, 600 total cumulative.

- M6-03 IndexedDB pending queue, synchronize permitted answers, visible status.

- M6-04 Attempt restored after reconnect/restart; timer budget persisted; worker idempotent.

- M6-05 Handle server outage separately + operator incident compensation.

- M6-06 Atomic permission for proctor-approved device switch.

Done: limits cannot be reset by reconnect; after cap expires timer resumes, no late unauthorized answer accepted; restart does not duplicate attempt/score.

### M7. Monitoring, proctor actions, reports

- M7-01 Proctor assignment or teacher self-monitor; WebSocket with origin auth and role scoping.

- M7-02 Student status monitoring, connection indicators, tab visibility as indication only.

- M7-03 Reset session, approve device switch, extend time with required reason and audit.

- M7-04 Announcements persisted & delivered after reconnect.

- M7-05 Teacher grade list/export XLSX; result display and review policies separate.

Done: instructor can run simultaneous exams, proctor cannot access unassigned ones, events recover after websocket disconnect, export values match DB grading.

### M8. Desktop Control Center, backups, offline installation

- M8-01 PySide6 overview, setup wizard, health/CPU/RAM/storage, logs redaction.

- M8-02 Network preflight: local DNS/TLS, allowlist, independently verify WAN+IPv6 block from student network.

- M8-03 Backup daily and manual, verification manifest and restore rehearsal.

- M8-04 Signed installer where feasible, startup services, upgrade/migration rollback.

- M8-05 Admin guide, teacher quickstart, proctor incident SOP.

Done: a nondeveloper operator can install/start/check/backup from GUI; service survives GUI closure; restore on isolated test clone proven.

### M9. End-to-end QA, performance, security & school pilot

- M9-01 Unit/integration/contract/E2E full regression, accessibility and mobile.

- M9-02 Security audit: authn/authz, BOLA, XSS import, CSRF, TLS, secret scan, network IPv4/IPv6 deny.

- M9-03 Load testing 30 simultaneous student attempts, 2 exams, burst answer save+submit.

- M9-04 Chaos test: Wi-Fi drop, browser refresh, server kill, disk full, DB restart, power recovery SOP.

- M9-05 Pilot with teacher using practice test, no actual sensitive student data until approval.

- M9-06 Post-pilot issue triage, release checklist, release notes/operator support.

Done: no critical security/answer integrity bugs; quantified p95; backup restore test, LAN WAN-off test, 30 simultaneous test passed on actual proposed hardware.

## 5. Test matrix and evidence

- T-001 | Type: E2E offline; Procedure: Put WAN off during 30-user exam; Pass criteria: Quiz flows continue via LAN, assets local

- T-002 | Type: Concurrency; Procedure: Two near-simultaneous start calls; Pass criteria: Only one attempt row

- T-003 | Type: Durability; Procedure: Save → ACK → kill browser/service; Pass criteria: ACK answer remains in DB after recovery

- T-004 | Type: Timing; Procedure: Reset browser device clock ±2h; Pass criteria: Timer unchanged server-side

- T-005 | Type: Pause per incident; Procedure: Disconnect > 5min; Pass criteria: Credited pause capped 300s; timer resumes

- T-006 | Type: Pause cumulative; Procedure: Repeat disconnect 3×; Pass criteria: Total credit never exceeds 600s

- T-007 | Type: Device switch; Procedure: Login other device w/o approval; Pass criteria: Denied; old attempt not reset

- T-008 | Type: Queue cutoff; Procedure: Sync queued answer after valid cutoff; Pass criteria: Reject/quarantine, never silent grade

- T-009 | Type: Submit retry; Procedure: Replay idempotency key 5×; Pass criteria: One submit result/receipt

- T-010 | Type: Object auth; Procedure: Student fetch other attempt; teacher other teacher exam; Pass criteria: Denied with safe response

- T-011 | Type: Score visibility; Procedure: TEACHER_ONLY vs IMMEDIATE vs AFTER_PUBLICATION; Pass criteria: Student API obeys policy

- T-012 | Type: Review visibility; Procedure: Show score but hide review keys; Pass criteria: Keys remain absent from API

- T-013 | Type: Question shuffle; Procedure: Shuffle option orders; Pass criteria: Grading still based on stable ID

- T-014 | Type: Category answer; Procedure: Mark some statements unanswered; Pass criteria: Partial score matches approved formula

- T-015 | Type: XLSX import; Procedure: Duplicate NIS / invalid rows; Pass criteria: Error report, no silent partial writes

- T-016 | Type: DOCX import; Procedure: Invalid table or suspicious file; Pass criteria: Safe parse failure, no macro execution

- T-017 | Type: Health; Procedure: Kill service / DB unavailable; Pass criteria: Status red, actionable error, no false green

- T-018 | Type: Service lifecycle; Procedure: Close PySide6 during exam; Pass criteria: Backend continues

- T-019 | Type: Backup; Procedure: Snapshot + corrupt simulation + restore test; Pass criteria: DB/media intact, manifest verified

- T-020 | Type: Network; Procedure: Student tries WAN IPv4/IPv6 and staff VLAN; Pass criteria: Only CBT and required infrastructure reachable

- T-021 | Type: Proctor permissions; Procedure: Unassigned user tries extend time; Pass criteria: Denied & audited

- T-022 | Type: Tab visibility; Procedure: Switch tabs and inspect audit; Pass criteria: Recorded as indicator, no automated guilty verdict

- T-023 | Type: Accessibility; Procedure: 360px mobile, keyboard nav, 200% zoom; Pass criteria: No lost controls/click traps

- T-024 | Type: Multi teacher; Procedure: Two teachers edit own bank, 2 exams live; Pass criteria: No cross-tenant/role leakage

- T-025 | Type: Grade numeric; Procedure: Rounding + MCMA all/none/wrong combinations; Pass criteria: Exact fixtures school-approved

Evidence storage: CI job URL/commit SHA, screenshots UI E2E, API contract validation, k6/Locust result (pick one), log excerpts scrubbed, router test transcript, restore drill proof, release checklist signed by product+teacher+operator.

## 6. Quality engineering dan CI gates

PR checks: format, lint, static typing, unit+integration tests, OpenAPI schema lint, migration forward test, dependency audit, secret scanner, front-end accessibility smoke, non-functional regression on critical pathways.

Release checks: clean install Win/macOS, pilot LAN offline, backup restore on clone, performance 30 users, threat-model signoff, no known critical/high reachable vulnerability without mitigation and explicit approval. Ujian tidak boleh diklaim aman hanya karena UI berfungsi.

Regresi fitur: sebelum merge behavior changes, cross-check PRD.md rule IDs, API spec, ERD migration, docs screen states, and test fixtures. Revisi business rules harus diputuskan manusia, bukan otomatis oleh coding agent.

## 7. Security checklist

- ☐ Cookie auth aman HttpOnly, Secure, SameSite; CSRF verified for mutations.

- ☐ Password hashed with Argon2id; login/token brute force mitigated; no shared default password.

- ☐ Per-object authorization (bank, exam, attempt, report, proctor action) tested.

- ☐ No answer key or hidden grade leaked via student APIs/websocket/cache.

- ☐ Upload DOCX/XLSX/image sanitized, limits, no code execution or SVG script.

- ☐ XSS + CORS/CSP + websocket Origin correctly restricted.

- ☐ No credentials/PII in log, crash dump, repository, client bundle.

- ☐ Network VLAN allowlist and WAN denial verified IPv4+IPv6.

- ☐ Package dependencies locked; SBOM/dependency scan; installer provenance.

- ☐ Backups encrypted, least-privilege restore controls, integrity checked.

- ☐ Audit events for extension, session reset, switch device, publish, restore.

## 8. UX and functional checklist

- ☐ Teacher, proctor, student, server operator flows tested end-to-end.

- ☐ Question type radio/MCMA checkbox/category are semantically correct.

- ☐ Student mobile touch targets >=44px; desktop keyboard navigation available.

- ☐ saving / persisted / queued offline / sync failed distinct states.

- ☐ Review mark independent of answered; submit warning counts are accurate.

- ☐ Loading/error/empty/expired/unauthorized states all handled.

- ☐ Timer and pause display consistent with server values.

- ☐ Result and review release policies independent and obeyed.

- ☐ No added features outside v1.0 without product approval.

## 9. Risk register

- R-01 | Risk: Offline queue sends past deadline; Likelihood / Impact: High / High; Owner: Backend+school; Mitigation: Define fair cutoff policy; label unsynced; reject & escalate

- R-02 | Risk: HP uses mobile data; Likelihood / Impact: High / Medium; Owner: School/proctor; Mitigation: Supervision policy; never claim perfect lockdown

- R-03 | Risk: Free pause abused by repeated disconnect; Likelihood / Impact: Medium / High; Owner: Backend/security; Mitigation: Server-accounted 5m/incident, 10m total, audit

- R-04 | Risk: PostgreSQL service install on macOS/Windows complex; Likelihood / Impact: Medium / High; Owner: Infra; Mitigation: Early spike, installer tests, consider policy-approved variant

- R-05 | Risk: HTTPS trust breaks BYOD onboarding; Likelihood / Impact: High / High; Owner: Infra; Mitigation: Validate certificate onboarding early and across devices

- R-06 | Risk: DB failure/power cuts during exam; Likelihood / Impact: Medium / Critical; Owner: Infra; Mitigation: UPS guidance, durable ack, backup, operational incident SOP

- R-07 | Risk: Multi-teacher object leakage; Likelihood / Impact: Medium / High; Owner: Security; Mitigation: Authorization test for every object query/route

- R-08 | Risk: Grading formula disputed; Likelihood / Impact: High / High; Owner: Product+school; Mitigation: Freeze rubric in exam snapshot; signoff fixtures

- R-09 | Risk: LAN congested with 30 clients; Likelihood / Impact: Medium / High; Owner: Infra/QA; Mitigation: WLAN survey, test load on real switches/AP

- R-10 | Risk: Scope creep before pilot; Likelihood / Impact: High / Medium; Owner: Product owner; Mitigation: v1.0 fixed scope, v1.5/v2.0 backlog separation

## 10. Decision log / pending stakeholder choices

- DEC-01 | What needs a decision: Scoring MCMA exact formula + category fraction precision/rounding; Current status: [OPEN] sekolah

- DEC-02 | What needs a decision: When offline queued answers arrive past server cutoff; Current status: [OPEN] sekolah/security

- DEC-03 | What needs a decision: Global server outage compensatory time; Current status: [OPEN] sekolah

- DEC-04 | What needs a decision: Operational hard-stop vs unrestricted individual duration for late starts; Current status: [OPEN] sekolah

- DEC-05 | What needs a decision: Hostname, TLS trust and router/VLAN topology; Current status: [OPEN] school IT

- DEC-06 | What needs a decision: Retention days, backup frequency destination and encrypted secret escrow; Current status: [OPEN] leadership

- DEC-07 | What needs a decision: Exact server OS/hardware/browser support baseline; Current status: [OPEN] survey/performance

- DEC-08 | What needs a decision: Caddy vs Nginx, PostgreSQL bundling vs separate install; Current status: [PROPOSED] infra spike

Rule: Decision Log tidak boleh diam-diam diisi oleh AI/coding agent tanpa bukti konsultasi stakeholder. Tautkan keputusan final kembali ke PRD+TDD+test fixtures.

## 11. Team workflow & definition of done

Perubahan kecil: 1 PR/issue, unit test, reviewer, update doc bila contract berubah. Perubahan besar: issue dengan FR/BR traceability, schema & migration, contract test, browser E2E, security review inline, release note.

DoD fitur: lint/types pass, tests automated, acceptance dari PRD terbukti, tidak ada secrets tersimpan, error/loading/empty state, akses role valid, API docs updated, accessible keyboard/mobile, observability, minimal manual demo, no regressions. Tidak mengharuskan penambahan tooling baru yang tidak diperlukan.

## 12. Post-v1.0 backlog (bukan janji roadmap)

- v1.5 kandidat: analytics kualitas soal, perbandingan kelas, essay grading manual, kartu ujian massal, PDF report, paket soal antarserver.

- v2.0 kandidat: SEB/kiosk pada platform kompatibel, integrasi router, standby server/HA, multi-school admin cloud opt-in.

- Research only: local AI opsional untuk analytics jika memberi manfaat nyata; ujian tetap bisa berjalan tanpa AI.

## 13. Release acceptance signature block

- Product owner: tujuan & ruang lingkup valid.

- Guru/kurikulum: kunci dan formula skor tervalidasi.

- Operator sekolah: instalasi, TLS, router, backup dan restore tervalidasi.

- Security reviewer: access controls, threat model, jaringan ujian, privacy review pass.

- QA lead: test matrix dan evidence sesuai gate.

Ready-to-build: Gate 0 selesai. Ready-to-pilot: M1–M8 lengkap dengan tests. Ready-to-release: M9 lulus tanpa blocker.